## Report
VENDOR VISIT REPORT
PVC Sealer — Robot Nozzle Choking (UBS) Investigation & Joint MoM
Ref | VVR/PVC-SEALER/2026-07
Report date | 28 Jul 2026
Meeting / Visit | Jul 2026 [confirm]
Vendor (audited) | Kansai Nerolac Paints Ltd (KNP)
Customer / Location | Maruti Suzuki India Ltd — Paint Shop A, Kharkhoda (PS-KA)
Product | PVC Sealer (UBS / underbody & seam sealer)
Application | Robot applicator (1 mm nozzle) + manual gun
FTIR reports shared with | M. Awasthi, A. Chaurasiya (MSIL)
Prepared by | [name / dept]
CONCERN
Recurring choking of 1 mm UBS robot nozzles with barrel-to-barrel variation. Visual check of the choke material shows tiny black particles, reddish-brown flakes, barrel-gasket chips, paint chips and black chips from the polyethylene bag, retained in barrels, filters and nozzles.
KEY FINDING
KNP's comparative FTIR of the choke particles vs. ALL suspected foreign particles showed NO IR match — but this is likely a FALSE NEGATIVE. After soaking in sealer, packaging absorbs plasticizer and is coated with a sealer film (carbonate / PVC) that masks and shifts its own bands, so virgin packaging will never match a soaked flake. NEW LEAD: the imported (Malaysia) RM packaging visually matches the choke flakes and is the prime suspect. Compare LIKE-FOR-LIKE — FTIR the packaging after matched sealer-soaking, and after solvent-extracting the flake to strip the sealer coat and recover the substrate; confirm the polymer by DSC / melt-point & TGA.
PRIORITY OPEN ACTIONS
1. Test the imported-Malaysia packaging correctly: soak a coupon in the same sealer (24–72 h, matching barrel residence) then FTIR, AND solvent-extract the choke flake to strip the sealer coat and FTIR the recovered substrate; add DSC / melt-point & TGA to ID the polymer independent of surface masking. Extend the RM-bag soak-FTIR test to the plastic liner.
2. Self-cleaning-filter residue vs FG report (04/08); metal brush (30/07); polythene for RM bags & FG barrel filling — fast-track.
3. Confirm larger UBS batch size (3–5 T); resolve whiteness (share cut-off batch); verify flow after modified batches 4137336 / 4145253.
SIGN-OFF
Prepared / MSIL |  | Reviewed / MSIL Quality | Acknowledged / KNP
Name: __________ |  | Name: __________ | Name: __________
Sign / Date: __________ |  | Sign / Date: __________ | Sign / Date: __________
Prepared from the joint MSIL–KNP MoM (tab: Issues), FTIR overlay and shop-floor sampling. Bracketed [ ] fields to be completed. The FTIR "no match" is against virgin suspected sources and is likely a soaking artifact; soak-matched / extraction-corrected FTIR plus thermal ID of the imported-Malaysia packaging is needed to confirm the source. See the 'Issues Tracker' sheet for the full action list.

## Issues Tracker
ISSUES & ACTION TRACKER — MSIL ⇄ KNP MoM
S.No | Section | Issue / Observation | Status / Remark | Status | Owner | Target
1 | Paint Shop — MSIL Kharkhoda (PS-KA) | Robot nozzle choking (UBS): tiny black particles in sealer batch; barrel-to-barrel variation; solid particles, barrel-gasket chips, paint chips; PE bag with black chips. | Comparative FTIR vs suspected particles — NO IR match (vs virgin refs; likely a soaking artifact). Action: test imported-Malaysia packaging soak-matched + solvent-extraction + DSC/TGA. | Open | KNP + MSIL
2 | Paint Shop — MSIL Kharkhoda (PS-KA) | Sealer flow / dripping on vehicles — manual sealer (viscosity 105 Pa·s). | Modified material batch to reach MSIL 27/07/26 — Batch 4137336. | Monitor | KNP | 27/07/26
3 | Paint Shop — MSIL Kharkhoda (PS-KA) | Sealer flow / dripping on vehicles — robot sealer / UBS (viscosity 110 Pa·s). | Modified material batch to reach MSIL 27/07/26 — Batch 4145253. | Monitor | KNP | 27/07/26
4 | Paint Shop — MSIL Kharkhoda (PS-KA) | UBS batch size 1 KL < sealer-line volume — hard to monitor batch-wise performance. Raise to 3–5 T for 3–4 days' consistency. | After internal discussion KNP to advise MSIL on bigger batch sizes. | Open | KNP
5 | Paint Shop — MSIL Kharkhoda (PS-KA) | Whiteness issue. | KNP to further improve and share the cut-off batch number. | Not resolved | KNP
6 | Paint Shop — MSIL Kharkhoda (PS-KA) | Baking-repair cracking — observed on 2 bodies after raising heat stabilizer 1.1% → 1.3%. | Resolved — no baking-repair crack after KNP countermeasure batch. | Resolved | KNP | Closed
7 | KNP Plant Audit | Hopper cleaning found OK — strengthen the cleaning process further. | Implemented. | Implemented | KNP | Done
8 | KNP Plant Audit | Corrugated sheet to be removed from pallets. | Implemented — corrugated sheet eliminated from process. | Implemented | KNP | Done
9 | KNP Plant Audit | Replace wooden brush with metal brush. | Aluminium-handle brush to be provided. | Open | KNP | 30/07/26
10 | KNP Plant Audit | Remove cardboard lid of standard-weight keeping box; replace with metal lid. | Implemented — cardboard lid removed from shopfloor, metal lid in use. | Implemented | KNP | Done
11 | KNP Plant Audit | RM packaging improvement: current powder bags → polythene bags (check with central purchase & supplier). | Under exploration with purchase & supplier. | Open | KNP + Purchase
12 | KNP Plant Audit | Increase filter-cleaning frequency from once to twice per week. | Implemented from 28/07/26. | Implemented | KNP | 28/07/26
13 | KNP Plant Audit | Test self-cleaning-filter residue and compare with FG. | Report to be shared by KNP. | Open | KNP | 04/08/26
14 | KNP Plant Audit | Soak paper pieces of RM bags in sealer for 24 h and test by FTIR. | Under testing — report to follow (next day). | Under test | KNP | Next day
15 | KNP Plant Audit | Use polythene for sealer filling inside barrels. | Vendor to be explored; procurement & implementation of polythene in FG filling on fast track. | Open | KNP | Fast-track
16 | KNP Plant Audit | Barrel cleaning found OK — strengthen the cleaning process further. | Implemented. | Implemented | KNP | Done
17 | KNP Plant Audit | Shop-floor area cleaning found OK — clean sticky areas and improve. | Implemented. | Implemented | KNP | Done
Status summary (snapshot as of report date):
|  | Total items | 17
|  | Implemented | 6
|  | Resolved | 1
|  | Monitor | 2
|  | Under test | 1
|  | Open | 6
|  | Not resolved | 1